Azure Implementation Brief

FSR Bidding Calculator — Post-Beta Deployment

| Prepared for | IT Department · Facilities & Security Department Leadership |
| --- | --- |
| Organization | FlixBus / Greyhound North America |
| Document type | Technical Implementation Brief — Post-Beta |
| Scope | Azure Static Web App → Full Azure Backend (App Service + SQL + AAD SSO) |
| Prerequisites | Completed SharePoint beta testing · IT sign-off on Azure subscription access |
| Classification | Internal · Confidential |

# 1. Executive Summary

The FSR Bidding Calculator has completed SharePoint-based beta testing. This brief defines the two-phase path from the current single-file HTML tool to a fully hosted, authenticated, database-backed Azure platform.

Phase A (immediate) deploys the existing HTML file as an Azure Static Web App — a zero-backend step that provides a clean HTTPS URL, removes the download-and-open friction, and enables controlled rollout to all agents without IT managing file distribution.

Phase B (Q3 2026, aligned with the 12-Month Roadmap) deploys the full backend stack: Azure App Service, Azure SQL Database, Azure AD SSO, and the Power BI reporting pipeline. This is the production-grade architecture described in the Product Roadmap document.

# 2. Beta Testing Outcomes & Readiness Assessment

## 2.1  What beta validated

- Calculator logic — bid comparison, benchmark calculation, Effort ($) variance, and approval routing all produce consistent, accurate results.

- FSR# auto-generation — sequential numbering (YYYY-NNN format) with localStorage persistence functions correctly across page refreshes and tab closures.

- CST date handling — request dates reflect America/Chicago time zone on page load, midnight rollover, tab restore, and at submission time.

- Print / PDF output — invoice-style print layout renders cleanly in Edge for email-based approval workflows.

- Data persistence — all form state, FSR Log, and theme preference survive browser refresh via localStorage.

- Special approval flags — Cameras, Signage, and Pest categories correctly bypass numeric approval thresholds.

## 2.2  Known limitations of the beta configuration (SharePoint)

| Limitation | Impact | Resolved by |
| --- | --- | --- |
| No shared database | Each agent has isolated FSR Log; no cross-agent visibility | Phase B — Azure SQL |
| No authentication | Anyone with the file can open it; no audit identity | Phase A adds URL control; Phase B adds AAD SSO |
| localStorage only | Data is lost if browser cache cleared or agent switches machines | Phase B — server-side persistence |
| Manual file distribution | IT must re-share file for every update | Phase A — single URL, instant updates |
| No Power BI integration | No cross-terminal spend reporting | Phase B — vw_fsr_report view + Power BI pipeline |

# 3. Phase A — Azure Static Web App Deployment

## Overview

Azure Static Web Apps (SWA) is a fully managed hosting service that serves static files (HTML, CSS, JS) over HTTPS with a globally distributed CDN. It costs nothing on the free tier for internal tools at this scale. No server configuration, no containers, no VMs.

This is the fastest path to a shared, reliable URL. Deployment takes under 15 minutes once IT has access to the Azure subscription. No backend changes to the HTML file are required.

## 3.1  Prerequisites for IT

- Access to the FlixBus / Greyhound Azure subscription (Contributor role on the target resource group, or Owner if creating a new resource group)

- Azure CLI installed on the deployment machine, or access to Azure Portal

- The file: FSR_Calculator_v3.html (provided post-beta)

## 3.2  Deployment steps — Azure Portal (no CLI required)

- Navigate to portal.azure.com → Create a resource → search "Static Web App" → Create.

- Fill in the basics:

  - Subscription: select the FlixBus / Greyhound subscription

  - Resource group: create new — fsr-calculator-rg

  - Name: fsr-bidding-calculator

  - Region: Central US (closest to CST operations)

  - Plan type: Free

  - Deployment source: Other (we deploy manually, not from GitHub)

- Click Review + create → Create. Wait ~60 seconds for provisioning.

- Once deployed, open the resource. Note the URL — it will be something like https://fsr-bidding-calculator.azurestaticapps.net

- In the Azure Portal, navigate to the Static Web App → Deployment → click "Upload" and upload FSR_Calculator_v3.html as index.html (rename the file on upload, or rename it before uploading).

- Open the URL in Edge. The calculator loads. Share this URL with all agents.

## 3.3  Deployment steps — Azure CLI (preferred for IT automation)

# Install the Static Web Apps CLI

npm install -g @azure/static-web-apps-cli

# Login to Azure

az login

# Create resource group

az group create --name fsr-calculator-rg --location centralus

# Create Static Web App

az staticwebapp create \

--name fsr-bidding-calculator \

--resource-group fsr-calculator-rg \

--location centralus \

--sku Free

# Deploy the HTML file (rename to index.html first)

cp FSR_Calculator_v3.html ./deploy/index.html

swa deploy ./deploy --env production

## 3.4  Custom domain (optional but recommended)

IT can map a custom subdomain such as fsr.flixbus.com or fsr-calc.greyhound.com to the Static Web App URL. This is done in Azure Portal → Static Web App → Custom domains and requires a CNAME record in your DNS provider. Certificate is provisioned automatically by Azure.

## 3.5  Access control

The free tier Static Web App does not natively enforce Azure AD authentication. For Phase A, access control options are:

- Leave the URL open (obscurity-only) acceptable for internal tools with no PII.

- Add Static Web Apps built-in auth with AAD provider — free tier supports this. Users must sign in with their Microsoft 365 account before accessing the page.

- Restrict to corporate IP range via Azure Front Door (requires Standard tier, ~$35/month additional).

Recommendation for Phase A: enable AAD authentication. Configuration steps:

- In Azure Portal → Static Web App → Authentication → Add provider → Microsoft (AAD).

- Set "Unauthenticated action" to "Redirect to login page."

- Users will be prompted to sign in with their FlixBus / Greyhound Microsoft account. No separate credentials.

# 4. Phase B — Full Backend Stack (Q3 2026)

## Overview

Phase B is the production architecture described in the 12-Month Product Roadmap. It adds a Node.js API backend (Azure App Service), a shared relational database (Azure SQL), Azure Active Directory SSO for identity and audit trails, and the Power BI reporting pipeline.

Phase B requires approximately 5 developer days using the provided backend code package. IT’s primary role is infrastructure provisioning and the Azure AD App Registration — the only task that requires admin-level Azure access.

## 4.1  Architecture diagram

| CLIENT FSR Calculator (HTML) Azure Static Web App | API Node.js / Express Azure App Service (B1) | DATA Azure SQL (S0) + Power BI pipeline |
| --- | --- | --- |

Additional services: Azure Function App (nightly Excel sync, vendor scoring), Azure Logic Apps (approval routing), Azure Active Directory (SSO + identity)

## 4.2  Resource provisioning checklist

| ✔ | Resource | SKU / Tier | IT action required |
| --- | --- | --- | --- |
| □ | Resource Group: fsr-prod-rg | N/A | Create in Azure Portal |
| □ | Azure App Service Plan | B1 (Basic) | Provision via Portal or CLI |
| □ | Azure App Service (Node.js 20) | B1 | Provision under the App Service Plan |
| □ | Azure SQL Server | Logical server | Provision; set admin credentials in Key Vault |
| □ | Azure SQL Database: fsr-db | S0 (10 DTU) | Provision under SQL Server |
| □ | Azure Function App | Consumption plan | Provision; link to Storage Account |
| □ | Azure Storage Account | Standard LRS | Required by Function App |
| □ | Azure Key Vault | Standard | Store DB connection strings + app secrets |
| □ | Azure Logic App | Consumption | For approval routing to Microsoft Teams |
| □ | AAD App Registration | — | ⚠️ Requires AAD Admin. See Section 4.3. |
| □ | Power BI Workspace | Pro license | Create workspace; connect to SQL view |

## 4.3  Azure AD App Registration (critical path item)

⚠️  This is the only step that requires Azure Active Directory admin permissions. It must be completed before developers can begin backend integration. All other provisioning tasks can proceed in parallel.

The App Registration gives the FSR Calculator its identity in Azure AD, enabling SSO so agents log in with their company Microsoft credentials.

- In Azure Portal → Azure Active Directory → App registrations → New registration.

- Name: FSR Bidding Calculator

- Supported account types: Accounts in this organizational directory only (single tenant).

- Redirect URI: Web → https://fsr-bidding-calculator.azurestaticapps.net (update when custom domain is set)

- Click Register. Note the Application (client) ID and Directory (tenant) ID — share these with the developer.

- Under Certificates & secrets → New client secret → set expiry to 24 months → Add. Copy the secret value immediately (it is only shown once) and store it in Azure Key Vault.

- Under API permissions → Add permission → Microsoft Graph → Delegated → add User. Read and email. Click Grant admin consent.

The developer needs: Application (client) ID, Directory (tenant) ID, and client secret (retrieved from Key Vault). No other AAD admin involvement is required after this step.

## 4.4  Database schema deployment

The backend code package includes schema.sql. IT runs this once against the Azure SQL database after provisioning:

# Connect to Azure SQL using sqlcmd or Azure Data Studio

sqlcmd -S fsr-sql-server.database.windows.net \

-d fsr-db \

-U <admin-user> \

-P <admin-password> \

-i schema.sql

This creates four tables (cities, services, fsr_requests, fsr_bids) and the vw_fsr_report view used by Power BI. No manual table creation is needed.

## 4.5  Application deployment

The backend code package (fsr-backend.zip) contains a Node.js Express API. Deployment to Azure App Service:

# Unzip the package

unzip fsr-backend.zip -d fsr-backend

cd fsr-backend

# Configure environment variables (also set these in Azure App Service > Configuration)

# Required variables:

# AZURE_SQL_CONNECTION_STRING  — from Key Vault

# AZURE_AD_CLIENT_ID           — from App Registration

# AZURE_AD_TENANT_ID           — from App Registration

# AZURE_AD_CLIENT_SECRET        — from Key Vault

# Deploy to Azure App Service

az webapp deployment source config-zip \

--resource-group fsr-prod-rg \

--name fsr-api \

--src fsr-backend.zip

## 4.6  Power BI connection

- In Power BI Desktop → Get Data → Azure → Azure SQL Database.

- Server: fsr-sql-server.database.windows.net · Database: fsr-db

- Select DirectQuery initially for setup; switch to Import (scheduled refresh every 15 min) for production to avoid contention with live FSR saves.

- Select the vw_fsr_report view. This flat view contains all fields needed for dashboards: FSR#, date, city, state, city multiplier, service category, lowest bid, benchmark, Effort ($), diff label, bid count, vendors, approval status.

- Publish to Power BI Service → share the workspace with Facilities and Procurement leadership.

5. Environment Variables Reference

All secrets must be stored in Azure Key Vault and referenced by the App Service via managed identity. Never hardcode credentials in the codebase.

| Variable name | Source | Description |
| --- | --- | --- |
| AZURE_SQL_CONNECTION_STRING | Key Vault | Full ADO.NET connection string for fsr-db |
| AZURE_AD_CLIENT_ID | App Registration | Application (client) ID from AAD |
| AZURE_AD_TENANT_ID | App Registration | Directory (tenant) ID from AAD |
| AZURE_AD_CLIENT_SECRET | Key Vault | Client secret — 24-month expiry, rotate before expiry |
| SHAREPOINT_SITE_URL | SharePoint Admin | URL of the SharePoint site hosting the Excel price file |
| SHAREPOINT_FILE_ID | SharePoint Admin | Drive item ID of the FSR pricing Excel workbook |
| GRAPH_CLIENT_ID | App Registration | Same as AZURE_AD_CLIENT_ID (used by Excel sync Function) |
| TEAMS_WEBHOOK_URL | Teams Admin | Incoming webhook URL for approval card routing |
| NODE_ENV | Manual | Set to "production" on App Service, "development" locally |

# 6. Azure Cost Summary

| Resource | Phase A | Phase B | Notes |
| --- | --- | --- | --- |
| Azure Static Web App | Free | Free | Continue hosting the front-end in Phase B |
| Azure App Service (B1) | — | ~$13/mo | Scale to B2 (>50 concurrent users) |
| Azure SQL Database (S0) | — | ~$15/mo | Upgrade to S2 if query volume grows |
| Azure Function App | — | ~$0/mo | Consumption plan, free at this call volume |
| Azure Key Vault | — | ~$1/mo | Standard tier, operations-based pricing |
| Azure Logic Apps | — | ~$5/mo | Approval routing, ~1,000 runs/month |
| Azure Storage Account | — | ~$1/mo | Required by Function App; minimal usage |
| Power BI Pro | — | $10/user/mo | Leadership + Procurement reporting users only |
| TOTAL (excl. Power BI) | Free | ~$35/mo | Well within standard departmental IT budget |

# 7. Security & Compliance Considerations

## 7.1  Data classification

The FSR Calculator processes vendor bid amounts, facility addresses, and service categories. This data is classified as Internal — not customer PII, not PCI, not HIPAA. Standard Azure security controls are sufficient.

## 7.2  Authentication & Authorization

- Phase A: Azure AD authentication on Static Web App (sign-in required before access)

- Phase B: Bearer token (JWT) validation on every API call via passport-azure-ad BearerStrategy

- Role separation: agents (read/write own FSRs), senior agents (approve), managers (full log access)

- No anonymous API access permitted in Phase B

## 7.3  Secrets Management

- All credentials stored in Azure Key Vault — never in source code or App Service config UI directly

- App Service accesses Key Vault via system-assigned managed identity (no credential rotation needed for that link)

- Client secret (24-month expiry): set a calendar reminder 60 days before expiry to rotate

## 7.4  Network

- Azure SQL: firewall rule to allow only the App Service outbound IP range; block all other inbound

- App Service: HTTPS-only enforced; minimum TLS 1.2

- Consider Azure Private Endpoint for SQL in Phase B if the organization requires data to stay off the public internet

# 8. Rollback & Continuity Plan

The HTML file is fully self-contained and functional without any backend. If Azure infrastructure is unavailable for any reason, agents can revert to running the file locally from SharePoint within minutes. No data entry capability is lost.

| Scenario | Impact | Recovery action |
| --- | --- | --- |
| Phase A Static Web App outage | Agents cannot access URL | IT re-shares HTML file via SharePoint link (5 min) |
| Phase B App Service outage | Calculator reverts to localStorage mode automatically | HTML front-end detects API unavailability and degrades gracefully |
| Phase B SQL Database outage | No new FSRs saved to shared DB | FSRs save to localStorage; bulk upload when DB restored |
| AAD client secret expired | SSO login fails for all users | Rotate secret in Key Vault; redeploy App Service config (< 30 min) |
| Accidental data deletion (SQL) | FSR Log data loss | Restore from Azure SQL automated backup (Point-in-Time Restore, 7-day window) |

# 9. Deployment Timeline

| Week | Phase | Milestone | Owner |
| --- | --- | --- | --- |
| Week 1 | Phase A | IT provisions Static Web App + uploads index.html | IT |
| Week 1 | Phase A | AAD authentication enabled on SWA | IT (AAD Admin) |
| Week 1 | Phase A | URL shared with all agents — full rollout | Facilities Ops |
| Week 2–3 | Phase B Prep | IT provisions: App Service, SQL, Function App, Key Vault | IT |
| Week 2–3 | Phase B Prep | AAD App Registration completed; credentials shared with developer | IT (AAD Admin) |
| Week 3–4 | Phase B Dev | Developer deploys backend API + schema.sql | Developer |
| Week 4–5 | Phase B Dev | HTML front-end updated to call API; localStorage fallback tested | Developer |
| Week 5 | Phase B Dev | Excel sync Function App deployed + tested | Developer |
| Week 6 | Phase B QA | End-to-end testing: SSO, FSR submission, DB persistence, print | IT + Facilities Ops |
| Week 7 | Phase B Go-live | Power BI Dashboard v1 connected to vw_fsr_report view | Analytics / IT |
| Week 7 | Phase B Go-live | Production go-live — localStorage mode retired | All stakeholders |

# 10. Contacts & Immediate Next Steps

## 10.1  Action items for IT — Start Immediately

| ✔ | Action | Est. time | Dependency |
| --- | --- | --- | --- |
| □ | Provision Azure Static Web App in fsr-calculator-rg | 15 min | Azure subscription access |
| □ | Upload FSR_Calculator_v3.html as index.html | 5 min | File received from Facilities team |
| □ | Enable AAD authentication on Static Web App | 10 min | AAD Admin access |
| □ | Share URL with Facilities & Security department | 5 min | Deployment complete |
| □ | Complete AAD App Registration (Phase B critical path) | 20 min | AAD Admin access |
| □ | Provision Phase B resources (App Service, SQL, Key Vault) | 45 min | Azure subscription access |

## 10.2  Documents Already Prepared

- FSR_Calculator_v3.html — production-ready front-end file (post-beta)

- FSR_Backend_Code.zip — Node.js API with schema.sql, Excel sync Function, and environment variable template

- FSR_12Month_Product_Roadmap.docx — full strategic context and Q3–Q2 2027 delivery plan

## 10.3  Questions & Escalation

For questions on this brief, contact the Facilities & Security Department. For Azure subscription access or AAD Admin tasks, escalate to the IT Cloud Infrastructure team using the standard Azure access request process.

# Appendix A — SQL Schema Overview

The following tables are created by schema.sql. No manual DDL is required.

| Table / View | Key columns | Purpose |
| --- | --- | --- |
| cities | city_id, city, state, tier, multiplier | Master city index; synced nightly from SharePoint Excel |
| services | service_id, category, subtype, unit, low, med, high, travel | Master service catalog; synced nightly from SharePoint Excel |
| fsr_requests | fsr_id, fsr_number, agent_id, city_id, priority, status, created_at | One row per FSR submission |
| fsr_bids | bid_id, fsr_id, vendor_name, bid_amount, is_lowest | One row per vendor bid; FK to fsr_requests |
| vw_fsr_report | Flat join of all tables + calculated Effort, diff, approval_level | Power BI source view; never write to this |

# Appendix B — API Endpoint Summary

Backend exposes the following REST endpoints. All require valid Azure AD bearer token in Authorization header.

| Method | Endpoint | Auth required | Description |
| --- | --- | --- | --- |
| GET | /api/cities | Bearer token | Returns all active cities with tier and multiplier |
| GET | /api/services | Bearer token | Returns full 244-service catalog |
| POST | /api/fsr | Bearer token | Saves a new FSR submission to Azure SQL |
| GET | /api/fsr | Bearer token | Returns all FSRs visible to the authenticated agent |
| GET | /api/fsr/:id | Bearer token | Returns a single FSR by ID |
| GET | /api/report | Bearer token (Manager) | Returns vw_fsr_report data for Power BI / export |
| POST | /api/vendor/score | Bearer token (Manager) | Triggers vendor scorecard recalculation (Q4 feature) |

# Document Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| FST Lead |  |  |  |
| IT Cloud Infrastructure Lead |  |  |  |
| Procurement Lead |  |  |  |
| Department Director |  |  |  |